## Risk Treatment Plan
DesertTech Solutions — Risk Treatment Plan
Risk ID | Risk | Existing Controls | Recommended Controls | Risk Owner | Target Date | Status | Residual Risk
R-001 | Phishing attacks | Antivirus | MFA, Email Filtering, Awareness Training | IT Manager | 31 Aug 2026 | In Progress | Medium
R-002 | Weak passwords | Password Policy | Password Manager, MFA | IT Manager | 15 Aug 2026 | Planned | Low
R-003 | Ransomware | Antivirus | Offline Backups, EDR | Infrastructure Lead | 30 Sep 2026 | Planned | Medium
R-004 | Unauthorized access | User Accounts | RBAC, Quarterly Access Reviews | IT Manager | 20 Aug 2026 | In Progress | Low
R-005 | Lost laptops | Device Lock | Full Disk Encryption | IT Support Lead | 10 Aug 2026 | Completed | Low
R-006 | Insider threat | HR Screening | User Activity Monitoring | HR Manager | 15 Sep 2026 | Planned | Medium
R-007 | Data leakage | Access Control | Data Loss Prevention (DLP) | Security Manager | 30 Sep 2026 | Planned | Medium
R-008 | Unpatched systems | Monthly Updates | Automated Patch Management | System Administrator | 15 Aug 2026 | In Progress | Low
R-009 | Cloud misconfiguration | Manual Reviews | Cloud Security Baseline | Cloud Administrator | 30 Aug 2026 | Planned | Medium
R-010 | Third-party security risk | Vendor Contracts | Vendor Security Assessments | Procurement Manager | 30 Sep 2026 | Planned | Medium