## Control Implementation Tracker
DesertTech Solutions — Control Implementation Tracker
Control ID | Control Description | Owner | Implementation Status | Evidence | Review Date | Comments
C-001 | Enable Multi-Factor Authentication | IT Manager | Completed | MFA Configuration Screenshot | 31 Jul 2026 | Successfully deployed
C-002 | Employee Security Awareness Training | HR Manager | In Progress | Attendance Records | 15 Aug 2026 | Annual training cycle
C-003 | Daily Server Backups | Infrastructure Lead | Completed | Backup Logs | 31 Jul 2026 | Restore test passed
C-004 | Password Policy Enforcement | IT Manager | Completed | Group Policy Screenshot | 31 Jul 2026 | Minimum 14 characters
C-005 | Monthly Patch Management | System Administrator | In Progress | Patch Compliance Report | 15 Aug 2026 | Critical servers updated first
C-006 | Quarterly Access Review | IT Manager | Planned | Access Review Checklist | 30 Sep 2026 | First review scheduled
C-007 | Endpoint Encryption | IT Support Lead | Completed | BitLocker Report | 31 Jul 2026 | All company laptops encrypted
C-008 | Email Filtering | Security Manager | In Progress | Email Gateway Report | 30 Aug 2026 | Anti-phishing rules enabled
C-009 | Vendor Risk Assessment | Procurement Manager | Planned | Vendor Assessment Forms | 30 Sep 2026 | High-risk vendors first
C-010 | Incident Response Exercise | Security Manager | Planned | Exercise Report | 15 Oct 2026 | Tabletop exercise planned